## Time_Line
EMBEDDED DESIGNS SERVICES INDIA (P) LTD
Project Name : |  | AIS_140
Date : |  | 2026-05-23
Doc Version : |  | 00.00.00
Serial No. | Device | Task | Discription | Time(in Min) | Start Date | End Date | Responsible Person | Status | Remark
1 | BASIC | Understanding of given documents releated to project | To obtain a clear understanding of the project requirements from the documentation. | 480 | 2026-05-23 | 2026-05-23 | Jeevan N M | Done
2 | Genrating the code by cubemX | Generating code from cubemx for new micro | Proper generatation of code using cubemx | 480 | 2026-05-25 | 2026-05-25 | Jeevan N M | Done
3 | GPIO & Code formating | Intializing the GPIO and formating code clearly | To access the pins of microcontroller | 480 | 2026-05-26 | 2026-05-26 | Jeevan N M | Not Started
4 | GPRS | Implement GPRS part | To do Network connection | 480 | 2026-05-27 | 2026-05-27 | Jeevan N M | Not Started
5 | SMS & GNSS | Implementation of SMS Section | To manage SMS service | 240 | 2026-05-28 | 2026-05-28 | Jeevan N M | Not Started
|  | Implementation of GNSS Section | To obtain GNSS data from module | 240 | 2026-05-28 | 2026-05-28 |  | Not Started
6 | TCP | Implementation of TCP | To maintain server communication | 480 | 2026-05-29 | 2026-05-29 | Jeevan N M | Not Started
8 | SPI FLASH | Implementation of SPI flash | To maintaiin storage for backup | 480 | 2026-05-30 | 2026-05-30 | Jeevan N M | Not Started
9 | Sleep | Implementation of Sleep mode | To get device turn off when nothing to do | 480 | 2026-06-01 | 2026-06-01 | Jeevan N M | Not Started
9 | SPI MEMS | Implementation of Spi mems | To get the alerts from vehicle | 480 | 2026-06-02 | 2026-06-02 | Jeevan N M | Not Started
10 | FOTA | Implementation of FOTA | To do Software update via air | 960 | 2026-06-03 | 2026-06-04 | Jeevan N M | Not Started
11 | HARDWARE VALIDATION | Validate the complete hardware | Hardware validtion of all peripherals |  |  |  | Jeevan N M | Not Started
12 | APPLICATION END | Implementaion of application end Data | implmenting the code based on app data |  |  |  | Jeevan N M | Not Started